## Sheet1
Totals | 107 | 19 | 3 | 85
Priority | Category | Sub Category | Task Item | Status
| Paper | Intro | Proofread | Not Started
| Paper | Intro | Formatting | Not Started
| Paper | Intro | Diagrams | Not Started
| Paper | Background | Proofread | Not Started
| Paper | Background | Formatting | Not Started
| Paper | Background | Diagrams | Not Started
| Paper | Background | Extend | Not Started
| Paper | FR | Proofread | Not Started
| Paper | FR | Extend | Not Started
| Paper | FR | Formatting | Not Started
| Paper | FR | Diagrams | Not Started
| Paper | FR | Write Theory | Not Started
| Paper | FR | Write PsuedoCode | Not Started
| Paper | FR | Write Example | Not Started
| Paper | FR | Proofread | Not Started
| Paper | FR | Formatting | Not Started
| Paper | FR | Diagrams | Not Started
| Paper | R# Tree | Write Theory | Not Started
| Paper | R# Tree | Write PsuedoCode | Not Started
| Paper | R# Tree | Write Example | Not Started
| Paper | R# Tree | Proofread | Not Started
| Paper | R# Tree | Formatting | Not Started
| Paper | R# Tree | Diagrams | Not Started
| Paper | Experiments | Write Setup | Not Started
| Paper | Experiments | Write Metrics | Not Started
| Paper | Experiments | Write Results | Not Started
| Paper | Experiments | Write Analysis | Not Started
| Paper | Experiments | Proofread | Not Started
| Paper | Experiments | Formatting | Not Started
| Paper | Experiments | Diagrams | Not Started
| Paper | Conclusion | Write Summary | Not Started
| Paper | Conclusion | Write Extensions | Not Started
| Paper | Conclusion | Proofread | Not Started
| Paper | Conclusion | Formatting | Not Started
| Paper | Conclusion | Diagrams | Not Started
| Paper | Cover | Cover Page | Not Started
| Paper | Cover | Bind | Not Started
| Paper | Appendix | Write Appendix of Results | Not Started
| Paper | Submission | Submit | Not Started
| Experiments | Generate Data Set | Uniform 10,000 | Completed
| Experiments | Generate Data Set | Real 10,000 | Completed
| Experiments | Generate Data Set | Uniform 100,000 | Completed
| Experiments | Generate Data Set | Real 100,000 | Completed
| Experiments | Generate Index | Uniform 10,000 R* | Not Started
| Experiments | Generate Index | Real 10,000 R* | Not Started
| Experiments | Generate Index | Uniform 100,000 R* | Not Started
| Experiments | Generate Index | Real 100,000 R* | Not Started
| Experiments | Generate Index | Uniform 10,000 FR | Not Started
| Experiments | Generate Index | Real 10,000 FR | Not Started
| Experiments | Generate Index | Uniform 100,000 FR | Not Started
| Experiments | Generate Index | Real 100,000 FR | Not Started
| Experiments | Generate Index | Uniform 10,000 FR | Not Started
| Experiments | Generate Index | Real 10,000 FR | Not Started
| Experiments | Generate Index | Uniform 100,000 FR | Not Started
| Experiments | Generate Index | Real 100,000 FR | Not Started
| Experiments | Generate Index | Uniform 10,000 R# | Not Started
| Experiments | Generate Index | Real 10,000 R# | Not Started
| Experiments | Generate Index | Uniform 100,000 R# | Not Started
| Experiments | Generate Index | Real 100,000 R# | Not Started
| Experiments | Generate Query Plan | 30% Search | Completed
| Experiments | Generate Query Plan | 60% Search | Completed
| Experiments | Generate Query Plan | 90% Search | Completed
| Experiments | Run Experiments | Execute | Not Started
| Experiments | Experiment Scripts | Write | Not Started
| Experiments | Summary Results | Page Reads | Not Started
| Experiments | Summary Results | Execution Time | Not Started
| Experiments | Summary Results | Page Writes | Not Started
| Experiments | Summary Results | CPU Time | Not Started
| Experiments | Summary Results | Memory Footprint | Not Started
| Experiments | Summary Results | Index Size | Not Started
| Experiments | Excel Results | Output | Not Started
| Experiments | Generate Graphs | Generate | Not Started
| Experiments | Analysis | Analysis | Not Started
| Code | R-Tree | Add kNN Search | Completed
| Code | R-Tree | Save Index | Started
| Code | R*-Tree | ChooseLeaf Algorithm | Completed
| Code | R*-Tree | Split Algorithm | Completed
| Code | R*-Tree | Forced ReInsert | Completed
| Code | FR-Tree | Psuedo-code | Completed
| Code | FRe-Tree | Psuedo-code | Completed
| Code | R#-Tree | Psuedo-code | Not Started
| Code | R-Tree | Update Split to use Pair | Not Started
| Code | R*-Tree | Update Split to use Pair | Not Started
| Code | All Trees | Handle Deletion of Page in Cache | Completed
| Code | R-Tree | Deletion - Should reinsert node into tree not leaves | Completed
| Code | All Trees | Handle Addition of Page in Cache | Completed
| Code | All Trees | Update with Coorect Cache Usage | Completed
| Code | LRU Cache | Create | Completed
| Code | Highest Tree Level Cache | Create | Not Started
| Code | Level Proportional Cache | Create | Not Started
| Code | R#-Tree | Create | Not Started
| Code | FR-Tree | Create | Not Started
| Code | FRe-Tree | Create | Not Started
| Code | R-Tree | Test Build Index | Completed
| Code | R#-Tree | Test Build Index | Not Started
| Code | R*-Tree | Test Build Index | Started
| Code | FR-Tree | Test Build Index | Not Started
| Code | FRe-Tree | Test Build Index | Not Started
| Code | LRU Cache | Test | Not Started
| Code | Highest Tree Level Cache | Test | Not Started
| Code | Level Proportional Cache | Test | Not Started
| Code | R-Tree | Test Queries | Started
| Code | R#-Tree | Test Queries | Not Started
| Code | R*-Tree | Test Queries | Not Started
| Code | FR-Tree | Test Queries | Not Started
| Code | FRe-Tree | Test Queries | Not Started
| Code | R-Tree | Test Save Index | Not Started

## Sheet2 (hidden)
Not Started
Started
Completed